## Plan
Neighbourhood Alert Implementation Plan (CUSTOMER) |  |  | Links below to Zen Desk help centre if you cant view email; support@neighbourhoodalert.co.uk
Ref | Description | Explanitory notes | Resources | Action for | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Initiation Phase
| 1st Implementation meeting via conference call | Overview of implementation plan to review the requirement |  | VISAV/Client |  | X
1 | Supply Implementation Plan |  | Document - implementation_plan | VISAV |  | X
2 | Purchase Order received |  |  | Client |  | X
3 | Alert Licence Issued, Inc. Schedules 1,2 & 3 | Standard IP Licence | Document - Alert_system_owners_licence | VISAV/Client |  | X
4 | Supply web Standard Web Terms and Conditions | Agreed by members at sign up | Document - T&C V7.0 | VISAV/Client |  | X
5 | Supply Standard Data Processing agreement |  | Document - DPA | VISAV |  | X
6 | Alert Licence Signed |  |  | VISAV/Client |  |  | X
7 | DPA Signed |  |  | VISAV/Client |  |  | X
8 | Customer Implementation Team inc. super Users | Complete Tab on Implementation plan | Document - implementation_plan | Client |  | X
9 | Arrange online/onsite Implementation Meeting, supply agenda |  | Document - Agenda_Implementation_Meeting | VISAV/Client |  | X
10 | Online/onsite implementation meeting |  |  | VISAV/Client |  |  | X
11 | Agree Milestone Plan | Agree Live Date |  | VISAV/Client |  |  | X
12 | Design Responsibilites and Branding | If acceptable, simply find an existing layout/design that you like, provide us with some corporate images and any ideas, suggestions and let us put together a layout for you to approve (or not). If you don’t like it you could then look to finding a designer to produce a more prescribed design but I suspect that you may find this unnecessary. | Links to Existing Alert sites | VISAV/Client |  |  | X
13 | Agree System Domain Name(s) |  |  | VISAV/Client |  |  | X
14 | Agree registration process | Simple, Full, Business. Test registration by using the work "test" and a number after your surname. |  | VISAV/Client |  |  | X
15 | Cleansing Data (if data import required) | Data to be in standard format for import |  | Client |  |  | X
16 | Establish KML (polygon GIS files) requirements | Mapping files | Document - KML_Structure | Client |  |  | X
Development Phase
17 | VISAV Establish Development Site and Provide Access | URL Temp Domain - XXXX.neighbourhoodalert.co.uk |  | VISAV |  |  | X |  | X
18 | Establish access to live site via ICT system on client site | Test Access, maps, message sending & Voice relay |  | VISAV |  |  | X
19 | Test which webinar programes can be used on client system | For training and meetings |  | VISAV/Client
20 | Agree which Information Providers are default | Police, NHWN, Fire & Rescue, Local Authority etc. |  | Client |  |  | X
21 | Sign-off Protocols, Access agreements and "Rules & Convensions document" | Internal Rules & Convensions discussion | Document TVP Example - TVP_Rules_&_Conventions_V1 | Client |  |  | X
22 | Agree website content, who is providing/uploading | About us, FAQ's Contact us etc |  | VISAV/Client |  |  | X
23 | Force ITC Whitelist Alert URLs |  | List of all required urls (Rapport, Alert, Zendesk etc) | Client
24 | Import KML data for mapping | From client-provided KML files |  | VISAV / Client |  |  |  | X
25 | Agree Community Groups |  | Document - ContactGroupSheet | Client |  |  |  | X
Implementation Phase
26 | Test Administration Area and System Understanding |  |  | Client |  |  |  | X
27 | User Acceptance Testing (UAT) |  |  | Client |  |  |  | X
28 | Artwork Creation |  |  | VISAV / Client |  |  | X
29 | Deadline for Artwork Sign-Off |  |  | VISAV / Client |  |  |  | X
30 | Creation of Website Content, Welcome Pages, Privacy Policy, Links etc |  | Example V4 site | VISAV / Client |  |  |  | X
31 | Set up Community Groups |  |  | VISAV |  |  |  | X
32 | Super User Training online or onsite |  | V4 Training Centre | VISAV / Client |  |  |  |  | X
33 | Add Branding to Entire Site Including Email Templates |  |  | VISAV |  |  |  | X
34 | Send system transfer warning messages on incumbant system | Notice of change to new system |  | Client
35 | Compile initial welcome message text (imported users) |  | Text, Voice and email eg messages | VISAV / Client |  |  |  |  | X
36 | Send Messages in all Formats | Client to send with assistance from Alert Support |  | Client | [5 empty] | X
37 | Produce 'Snag List' |  |  | Client |  |  |  |  | X
38 | Resolve 'Snag List' |  |  | VISAV |  |  |  |  | X
39 | Final Security Testing of System |  |  | Client |  |  |  |  | X
40 | Key Stakeholders demo for Neighbourhood Inspectors and senior team (optional) |  |  | VISAV / Client |  |  |  | X
41 | Account request process for all remaining users | [6 empty] | X | X
42 | User Training online (& testing window) |  | V4 Training Centre | Client |  |  |  | X | X | X
43 | Go Live | Site is actually live earlier but this date is deadline for completion of tasks |  | All | [6 empty] | X
44 | Internal Campaign to Increase Users |  |  | Client | [6 empty] | X
45 | Add site map to web master tools |  |  | VISAV | [6 empty] | X
Note on V23: Rebrand Dev site with final design Build email template

## Team
Implementation Team
VISAV Ltd
Name | Role | Email | Office No. | Mobile No.
Chris Davis | Managing Director | chris@visav.co.uk | 0115 924 5517 Ex 223 | 07825 267191
Mike Douglas | Implementation / Training | mike@visav.co.uk | 0115 924 5517 Ex 224 | 07771 557788
Rob Nelson | Accounts / Support | rob@visav.co.uk | 0115 924 5517 Ex 231
Nick Houghton | Web Developer & System Support | nick@visav.co.uk | 0115 924 5517 Ex 241
Qamar Sheikh | IT Support | qamar@visav.co.uk | 0115 924 5517 Ex 225
Client